## Project Plan
Project Name | AI Copilot Go To Market Plan
Number | Task or Milestone | Task / Milestone | Date Due | Owner | Status | Notes | Files / Documents
1 | Product | Milestone |  | Jonathan Foy
1.1 | Enablement process for GTM org | Task | [ ] | Jonathan Foy | In Progress
1.2 | Ability to break out and turn on co-pilot by Channel | Task | 2024-09-27 | Jonathan Foy | Done | JF 9.22 Discussing with the team - might not need to be able to enable differently by channel, but most specifically need to have volume borken out by channel to bill accurately by customer. As part of enablement - we need to flag for finance which channels should count toward volume for the copilot. | Report Accessed Here
1.3 | User guide | Task | 2024-09-27 | Mark Harper | Done | Polly AI User Guide | Mark Harper - add link here to doc
1.4 | Team training for sales | Task | 2024-09-27 | Mark Harper | Done | Scheduled - 9/27
1.5 | Team training for Support, Success, AMs | Task | 2024-09-27 | Mark Harper | Done | Scheduled - 9/27
2 | Sales & Account Management | Milestone |  | James Schibli
2.1 | Pricing Strategy | Task | 2024-09-27 | Michael Chan / Joshua Krivisky | Done | See document to right | 2.0 AI Copilot Pricing and Commercial Terms
2.2 | Select beta customers | Task | 2024-09-20 | James Schibli | Done | Customer must have contract before going into beta James to add link with tracker of beta customers | See beta customers tab
2.3 | Determine free months for escalated customers | Task |  | James Schibli | Done | Certain customers per Adam C's sign off can go free through 4/1 with contract signed.
2.4 | Existing customer renewal and pricing strategy | Task | [ ] | James Schibli | Done | James working on outline - we are approaching all customers who want this with goal to renew. | James Schibli can you please link to upcoming renewal list?
2.5 | ROI Analysis and Talking points on cost savings analysis | Task | 2024-10-22 | Jacquelyn Studdert | Done | See ROI tab | finalize set for 10.22
2.6 | Develop BVA | Task | 2024-10-08 | Jacquelyn Studdert | Done
2.7 | Marketing collaters/materials for Sales | Task |  | Samantha MacKendrick | Done |  | (4) Polly - Artificial Intelligence (2024).pdf
2.8 | Talk track for sales | Task | 2024-10-31 | Samantha MacKendrick | Done | We need bullet point talk tracks for this. The email I sent to Brad from Van Dyk has some strong talking points in there that sales / Acct Mgmt can use
2.9 | 5 beta customers deployed by 11/1 | Task | 2024-11-01 | James Schibli | In Progress |  | James/Jon/Mike to meet later this week to prepare plans
3 | Operations | Milestone |  | John Levering
3.1 | Add product in salesforce | Task |  | Chase Wallace | Done
3.2 | Process to notify Success for Implementation | Task | 2024-10-18 | John Levering | Not Started | Done adhoc currently.
3.3 | Training for Customers | Task | 2024-10-15 | Mark Harper | Done | Lance/Maddy giving teach-back post 9/27 training (mid-October team ready to train customers as needed)
4 | Legal | Milestone |  | Colby Mangonon
4.1 | Draft Responsible AI policy | Task | 2024-09-27 | Colby Mangonon | Done
4.2 | Order form/Contract Lang | Task | 2024-09-27 | Colby Mangonon | Done |  | 2.0 AI Copilot Pricing and Commercial Terms
4.3 | MSA and Update to Exhibit A | Task | 2024-09-27 | Colby Mangonon | In Progress | Josh to check with Colby on MSA completeness
4.4 | Renewal Motion Clarity: Renewals need to get on current MSA | Task | 2024-10-31 | Colby Mangonon | Not Started | want clarity on goal: addendum to the order for, or getting on new MSA as a prereq for contracting on this product. - Colby / James to get clarity with Adam C - clarity needed - if when we restart a term, do we want to get them to a new MSA?
4.5 | Broad Desc of Product to drop into Exh. A | Task | 2024-10-16 | Jonathan Foy | Done | added 9.23
4.6 | Legal restrictions or addt. terms we want agreed to for engagement within AI | Task | 2024-10-25 | Jonathan Foy | In Progress | added 9.23
4.7 | [Patent Ready] | Task | [ ] | Colby Mangonon | Not Started
5 | Finance & Billing | Milestone |  | Joshua Krivisky
5.1 | Create table with volume and break out by Channel and Customer | Task |  | Jonathan Foy | Done | Changes to dashboard: -Set to UTC timezone -Make sure filters are correct -Download as monthly with customers as rows and months as columns -Split out by channel / org -Does not change retroactively (after a month has ended, no change to historical data) | Report Accessed Here
5.2 | Update Netsuite (new transaction item, etc.) | Task |  | Paul Yi | Done | Account summary 4040 AI Copilot Revenue and account 4043 Transaction Fees - AI Copilot created
5.3 | Maxio set up to receive transaction info and send invoices with regular monthly invoice | Task | 2024-09-27 | Syed Jafri | Done | Team to test this out.
5.4 | Add monthly tracking in Product Usage Summary workbook | Task |  | Paul Yi | Done
5.5 | Comission structure | Task | [ ] | John Levering / Josh | Done | Mo. minimum which is counting for ARR - this is good to go (10.7)

## Key Decisions
Key Decisions | Date | Parties Involved
We will split out and turn on Co-Pilot by Channel | 2024-09-17 | Jon, John, Josh, James, Jackie
AI-Co Pilot it turned on by Customer; Cannot be split out by LO | 2024-09-17 | Jon, John, Josh, James, Jackie
Charging will occur by initial lock volume | 2024-09-17 | Jon, John, Josh, James, Jackie
We have to have a contract executed before turning this product on | 2024-09-17 | Jon, John, Josh, James, Jackie

## ROIBVA Analysis
Inputs | Enter Customer Number | Salary Information | Annual | Hourly
Number of Loans Per Month | 200 | Processor | 40000 | 19.2308
Average Margin (basis points) | 1.5
Average Loan Size | 400000 | Loan officer | 75000 | 36.0577
number of loan officers | 20
Number of LOAs | 10 | Loan officer Assistant | 50000 | 24.0385
Number of Processors | 20
Average amount spent per day evaluating loan scenarios (hours)/week | 3
Output
% of LOA’s out of organization
% Processors out of organization
156 | Annual number of hours saved for each Loan Officer
Improved Margin of this amount due to revenue optimization
Critical Talking Points
Polly's AI solution not only provides loan officers faster evaluation to determine the best product and price for their borrowers, but it also fully encompasses our knowledge base giving your loan officers, capital markets team, and lock desk team an extra pair of "hands" to quickly decision and take action when they need assistance - reduce/eliminating the back and forth internally or with Polly support.
Recruiting/retention tool for branches and LO’s for the organization
Superior user experience and far more efficient

## Beta Customers
Beta Customers | [5 empty] | Note: The language in the contract is that we are under the assumption of a beta product until 4/1.
| Customer | Account Status | Target Start Date | Billing Start Date | Status | Notes & Feedback
1 | Resicentral | Non-escalated | 2024-11-01 |  | Signed | Takeaways - asking for some kind of lang. (JF needs to follow up with DISC ticket #)
2 | MLD Mortgage | Non-escalated | 2025-04-01 |  | Signed
3 | NAF | Non-escalated | TBD |  | Signed | James Schibli working with Adam on strategy
4 | Nova Home Loans | Non-escalated |  |  | Signed
5 | Stockton | Non-escalated | 2024-11-01
6 | Valon | Non-escalated | 2024-11-01
7 | EPM | Escalated | 2025-01-01
8 | Primis | Non-escalated | 2025-01-01
9 | Glacier | Escalated | 2025-01-01
10 | Greenway | Escalated | 2025-01-01
11 | Wintrust | Escalated | 2025-01-01
12 | AFR | Non-escalated | 2025-01-01
13 | Atlantic Coast | Non-escalated | 2025-01-01
14 | Ruoff | Non-escalated | 2025-04-01
15 | CNB Florida | Non-escalated | 2025-04-01
16 | PRMI | Escalated | 2025-04-01
17 | Southeast Mortgage | Escalated | 2025-04-01
18 | Go Mortgage | Non-escalated | 2025-04-01
19 | Vandyke | Non-escalated | 2025-04-01
20 | Movement | Non-escalated | TBD |  |  | James Schibli working with Adam on strategy
21 | PRMG |  | TBD |  |  | scheduling follow up with decision makers on demo
22 | 1st 2nd of NJ | Non-escalated