## Project Plan
Project Name | API Offering Go To Market Refresh Plan
Number | Task or Milestone | Task / Milestone | Date Due | Owner | Status | Notes | Files / Documents
1 | Product | Milestone |  | Jonathan Foy
1.1 | Enablement process for GTM org | Task | 2024-10-11 | Jonathan Foy | In Progress
1.2 | Ability to track API Volume by Customer by SKU | Task |  | Jonathan Foy | Done
1.3 | User guide | Task | 2024-10-11 | Mark Harper | In Progress | userguides are complete? | Mark Harper can you please update with link?
1.4 | Team training for sales | Task | 2024-11-15 | Mark Harper | In Progress
1.5 | Team training for Support, Success, AMs | Task | 2024-11-15 | Mark Harper | In Progress
2 | Sales & Account Management | Milestone |  | James Schibli
2.1 | Pricing Strategy | Task |  | Michael Chan / Joshua Krivisky | Done | See document to right | https://docs.google.com/spreadsheets/d/1Kqa5sZYDOWmIb-AKUSyfO24u_s0XG02S1Qpf_uLcqBI/edit?gid=1748885452#gid=1748885452
2.2 | Existing customer renewal and pricing strategy | Task |  | James Schibli | Done
2.3 | ROI Analysis and Talking points on cost savings analysis | Task |  |  | Done | See ROI tab
2.4 | Develop BVA | Task | [ ] | TBD | Not Started
2.5 | Marketing collaters/materials for Sales | Task |  | Samantha MacKendrick | Done |  | [ ]
2.6 | Talk track for sales | Task |  | Samantha MacKendrick | Need to Confirm | Samantha MacKendrick to add link to talk track here. | https://drive.google.com/file/d/1VRyx_6VWG0Ck-Mh0XGSRwoh4_PdcCFy3/view?usp=drive_link
3 | Operations | Milestone |  | John Levering
3.1 | Order form language | Task | [ ] | John Levering | Done
3.2 | Contract terms standardized | Task | [ ] | John Levering | Done
3.3 | Add product in salesforce | Task | 10.4 | John Levering | Done | Need to add Batch & Extensible Products
3.4 | Process to notify PS for Implementation | Task | TBD | John Levering | Under Review | Done for new logos; needs to be done for cross-sell
3.5 | Training for Customers | Task | [ ] | Mark Harper | Need to Confirm | Maybe a general overview webinar of API options and what they do?
4 | Legal | Milestone |  | Colby Mangonon
4.1 | MSA and Update to Exhibit A | Task | [ ] | Colby Mangonon | Need to Confirm
4.2 | Add reference to in MSA | Task | [ ] | Colby Mangonon | Need to Confirm
4.3 | Ensure order form conforms to docs | Task | [ ] | Colby Mangonon | Need to Confirm
4.4 | Clarity needed on API Skus | Task | 2024-09-27 | Jonathan Foy | Need to Confirm | do we need a different sku for iframe?
5 | Finance & Billing | Milestone |  | Joshua Krivisky
5.1 | Create report for API Volume by Customer by SKU | Task | 2024-10-28 | Jonathan Foy | In Progress | Report linked to left. Ticket submitted below to update report with columns for months, always set to UTC. Show all customer orgs https://pollyex.atlassian.net/browse/APP-13206 | https://54769f10cb894e03b4c9384f27639bf7.us-east-1.aws.found.io:9243/app/dashboards#/view/2aaf1300-5694-11ef-bbec-7790174c7873?_g=(filters:!(),refreshInterval:(pause:!t,value:60000),time:(from:now-30d%2Fd,to:now))
5.2 | Update Netsuite (new transaction item, etc.) | Task |  | Paul Yi | Done
5.3 | Maxio set up to receive transaction info and send invoices with regular monthly invoice | Task |  | Syed Jafri | Done
5.4 | Add monthly tracking in Product Usage Summary workbook | Task |  | Paul Yi | Done
5.5 | Comission structure | Task |  | Joshua Krivisky | Done

## Key Decisions
Key Decisions | Date | Parties Involved

## ROI Analysis
Scearnio API: Deploy the power of Polly's PPE to deliver accurate, data-driven pricing decisions, all directly within their branded experience or retail marketing site.
1 | Loan by Loan Pricing Comparison
2 | Run and display real-time pricing directly from marketing website
3 | Integrate with CRM to identify opportunities that drive bottom-line revenue
4 | Integrate accurate pricing into proprietary systems (in-house LOS, POS, etc).
5 | Supports both historical and current market pricing
Batch API: Proactively monitor and analyze loan pipeline pricing to identify opportunities to recapture business and re-engage existing clients.
1 | Monitor and manage servicing assets for lead recapture
2 | Create trust and a better overall borrower experience with existing clients
3 | Point-in-time API can be run at any frequency desired or required by lenders' unique business processes
Extensible API: This API supports all key functionality related to loan management and lock desk processes, from the initial rate lock through any post-lock actions.
1 | Attain consistent pricing and lock actions across the mortgage tech stack
2 | Supports a reprice, lock extensions, product changes, price exceptions, relocks, cancellations, and float requests
3 | Support worse case pricing and historical searches

## Beta Customers
Beta Customers
| Customer | Account Status | Target Start Date | Status | Notes & Feedback
n/a