## Project Plan
Project Name | Lender Intelligence Go To Market Refresh Plan
Number | Task or Milestone | Task / Milestone | Date Due | Owner | Status | Notes | Files / Documents
1 | Product | Milestone |  | Jonathan Foy
1.1 | Enablement process for GTM org | Task | 2024-10-25 | Jonathan Foy | In Progress
1.2 | User guide | Task | 2024-11-22 | Mark Harper | Done | https://connect.polly.io/hubfs/101-Training/Lender-Intelligence-User-Guide.pdf#toolbar=0
1.3 | Team training for sales | Task | 2024-11-22 | Mark Harper | Done
1.4 | Team training for Support, Success, AMs | Task | 2024-11-22 | Mark Harper | Done
2 | Sales & Account Management | Milestone |  | James Schibli
2.1 | Pricing Strategy | Task |  | Michael Chan / Joshua Krivisky | Done | See document to right | https://docs.google.com/spreadsheets/d/1Kqa5sZYDOWmIb-AKUSyfO24u_s0XG02S1Qpf_uLcqBI/edit?gid=1748885452#gid=1748885452
2.2 | Existing customer renewal and pricing strategy | Task |  | James Schibli | Done
2.3 | ROI Analysis and Talking points on cost savings analysis | Task |  |  | Done | See ROI tab
2.4 | Develop BVA | Task | [ ] | TBD | Not Started
2.5 | Marketing collaters/materials for Sales | Task |  | Samantha MacKendrick | Done |  | [ ]
2.6 | Talk track for sales | Task |  | Samantha MacKendrick | Need to Confirm
3 | Operations | Milestone |  | John Levering
3.1 | Order form language | Task | [ ] | John Levering | Done
3.2 | Contract terms standardized | Task | [ ] | John Levering | Done
3.3 | Add product in salesforce | Task | [ ] | John Levering | Done
3.4 | Process to notify PS for Implementation | Task | [ ] | John Levering | Under Review | Done for new logos; needs to be done for cross-sell
3.5 | Training for Customers | Task | [ ] | Mark Harper | In Progress | Potential webinar in December? If we want to include.
4 | Legal | Milestone |  | Colby Mangonon
4.1 | MSA and Update to Exhibit A | Task | [ ] | Colby Mangonon | Need to Confirm
4.2 | Add reference to in MSA | Task | [ ] | Colby Mangonon | Need to Confirm
4.3 | Ensure order form conforms to docs | Task | [ ] | Colby Mangonon | Need to Confirm
4.4 | Clarity needed on what LI means, Analytics etc. | Task | 2024-09-27 | Jonathan Foy | Need to Confirm
5 | Finance & Billing | Milestone |  | Joshua Krivisky
5.1 | Create report for Lender Intelligence Customer Tracking | Task | 2024-09-27 | Jonathan Foy | In Progress | Report does not exist today. Need by customer, # of seats monthly
5.2 | Need to be able to assign within app who can access Analytics (be as Analytics Seats) | Task | 2024-09-27 | Jonathan Foy | In Progress | Jon to work with eng on how we can flag for only specific defined users to access analytics
5.3 | Update Netsuite (new transaction item, etc.) | Task | [ ] | Paul Yi | Done
5.4 | Maxio set up to receive transaction info and send invoices with regular monthly invoice | Task | [ ] | Syed Jafri | Done
5.5 | Add monthly tracking in Product Usage Summary workbook | Task | [ ] | Paul Yi | Done
5.6 | Comission structure | Task | [ ] | Joshua Krivisky | Done

## Key Decisions
Key Decisions | Date | Parties Involved

## ROI Analysis
1
2
3
4
5

## Beta Customers
Beta Customers
| Customer | Account Status | Target Start Date | Status | Notes & Feedback
n/a